## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to Cyber Threat Detection & Dashboard Requirements Analysis | MUST HAVE | No Dependency | Chetna L Shapur | 3- Completed
S1 | S1 | US-001 | Project Workflow Design, System Architecture Diagram & Goal Documentation | MUST HAVE | Architecture Design | Chetna L Shapur | 3- Completed
S2 | S2 | US-001 | Agile Documentation Preparation (Sprint Plan, Defect Tracker, Test Cases) | MUST HAVE | No Dependency | Stuti Porwal | 3- Completed
S2 | S2 | US-001 | Research on Cyber Threat Types (Phishing, Malware, DDoS, IP Spoofing) | MUST HAVE | Research from AI Tools | Stuti Porwal | 3- Completed
S2 | S2 | US-001 | Dataset Collection & Preparation for Threat Analysis | MUST HAVE | Research Sources | Stuti Porwal | 3- Completed
S3 | S3 | US-001 | Frontend Setup using React/Vite for Dashboard UI | MUST HAVE | VS Code Setup | Stuti Porwal | 3- Completed
S4 | S4 | US-001 | Backend Setup (Node.js / API Creation for Threat Data Handling) | MUST HAVE | Node & Express | Stuti Porwal | 3- Completed
S5 | S5 | US-001 | Real-Time Threat Data Simulation & API Integration | MUST HAVE | Backend APIs | Stuti Porwal | 3- Completed
S6 | S6 | US-001 | Database Integration for Storing Threat Logs | MUST HAVE | Database Setup | Stuti Porwal | 3- Completed
S7 | S7 | US-001 | AI-Based Threat Prediction & Risk Scoring Implementation | MUST HAVE | ML Model | Stuti Porwal | 3- Completed
S8 | S8 | US-001 | Dashboard Visualization (Charts, Graphs, Live Threat Map) | MUST HAVE | Frontend + Backend | Stuti Porwal | 3- Completed
S9 | S9 | US-001 | Alert System Integration (IP Blocking, Incident Response Module) | MUST HAVE | Backend Logic | Stuti Porwal | 3- Completed
S10 | S10 | US-001 | Testing, Debugging & Performance Optimization | MUST HAVE | Complete System | Stuti Porwal | 3- Completed
S11 | S11 | US-001 | Final Demo Preparation & Presentation to Internal Team | MUST HAVE | PPT & Project | Stuti Porwal | 3- Completed
S11 | S11 | US-001 | Final Project Demonstration to Infosys Team | MUST HAVE | PPT & Project | Stuti Porwal | 3- Completed
Note on F2: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status
SPRINT 1 BACKLOG
US-001 | 1 | Requirement Gathering for Cyber Threat Dashboard | 2025-12-29 | 2025-12-30 | Chetna L Shapur | Build | 3- Completed
US-001 | 2 | Research on Cyber Threat Types (Phishing, Malware, DDoS) | 2025-12-30 | 2026-01-01 | Chetna L Shapur | Build | 3- Completed
US-001 | 3 | System Architecture & Workflow Design | 2026-01-02 | 2026-01-04 | Chetna L Shapur | Build | 3- Completed
SPRINT 2 BACKLOG
US-001 | 4 | Dataset Collection for Threat Logs | 2026-01-05 | 2026-01-07 | Chetna L Shapur | Others | 3- Completed
US-001 | 5 | Data Cleaning & Preprocessing | 2026-01-08 | 2026-01-09 | Stuti Porwal | System Test | 3- Completed
US-001 | 6 | Define Threat Fields (IP, Time, Severity) | 2026-01-10 | 2026-01-11 | Stuti Porwal | Coding | 3- Completed
SPRINT 3 BACKLOG
US-001 | 7 | Frontend Setup using React + Vite | 2026-01-12 | 2026-01-14 | Stuti Porwal | Coding | 3- Completed
US-001 | 8 | Dashboard UI Design (Sidebar, Cards, Layout) | 2026-01-15 | 2026-01-18 | Stuti Porwal | Design | 3- Completed
US-001 | 9 | Backend Setup using Node.js & Express | 2026-01-19 | 2026-01-22 | Stuti Porwal | Coding | 3- Completed
US-001 | 10 | Create REST APIs for Threat Data | 2026-01-23 | 2026-01-26 | Stuti Porwal | Design | 3- Completed
US-001 | 11 | Database Integration for Threat Logs | 2026-01-27 | 2026-01-30 | Stuti Porwal | System Test | 3- Completed
US-001 | 12 | Real-Time Threat Data Simulation | 2026-01-31 | 2026-02-03 | Stuti Porwal | System Test | 3- Completed
US-001 | 13 | AI-Based Risk Scoring & Severity Classification | 2026-02-04 | 2026-02-08 | Stuti Porwal | Design | 3- Completed
US-001 | 14 | Visualization (Charts, Graphs, Live Monitoring) | 2026-02-09 | 2026-02-14 | Stuti Porwal | Design | 3- Completed
US-001 | 15 | System Testing & Debugging | 2026-02-19 | 2026-02-22 | Stuti Porwal | Design | 3- Completed
US-001 | 16 | Documentation & PPT Preparation | 2026-02-23 | 2026-02-04 | Stuti Porwal | Design | 3- Completed
US-001 | 17 | Internal Audit Demonstration | 2026-02-25 | 2026-02-25 | Stuti Porwal | Design | 3- Completed
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016

## Stand Up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 3 | Day 10 | Frontend setup issue | Reinstalled dependencies and fixed configuration
Sprint 3 | Day 11 | API connection error | Corrected endpoint and enabled CORS
Sprint 3 | Day 12 | Database connection issue | Updated connection string and tested DB
Sprint 3 | Day 13 | Chart not displaying data | Fixed data format before rendering
Sprint 3 | Day 14 | Minor bugs in integration | Debugged and tested full system

## Retrospection
Sprint # | Sprint start date | Sprint end date | Team member name | Start doing | Stop doing | Continue doing | Action Taken
Sprint 1 | 2025-12-29 | 2026-01-04 | Stuti Porwal | Understanding project requirements and planning system design | Assuming requirements without confirmation | Maintaining proper documentation | Finalized project plan and architecture
Sprint 2 | 2026-01-05 | 2026-01-18 | Stuti Porwal | Developing backend, database, and core modules | Delaying testing until full completion | Writing structured and modular code | Successfully implemented backend and database integration
Sprint 3 | 2026-01-19 | 2026-02-09 | Stuti Porwal | Integrating frontend, backend, and visualization | Rushing deployment without validation | Testing after each development stage | Completed full system integration, testing, and documentation